## 1. Scope Analysis & Functional Decomposition

### Widget Point Count

- Input Widgets: Sensor Select Box (Combobox), Add Sensor (Pushbutton), Remove Sensor (Pushbutton), Start/Stop (Pushbutton), Sensor List selection (List) ->  5 widgets

- Describing Widgets: "Sensor Data Collector" title (Label), "Selected Sensors" header (Label) -> 2 widgets

- Composite Widgets: Selected Sensors list (Table/List) -> 1 widget

Calculation:

- Total Widgets = 5 + 2 + 1 = 8 widgets.

- Function Points (FP) = Total Widgets x  2 = 16 FP

## 2. Technical Size Estimation (LOC)

To estimate the coding effort, we convert the Function Points into Lines of Code (LOC). Since this is a mobile application, we will assume the use of Java, which has a conversion factor of 53 LOC per FP.

- 16  FP X  53  LOC/FP = 848  LOC

- Kilo Delivered Lines (KDL) = 0.848

## 3. Effort Estimation (COCOMO Model)

Using  COCOMO (Constructive Cost Model) to determine the effort in person-months (E).

### Step A: Nominal Effort (Ei)

The project is categorized as organic (simple) given it is a small-scale data collection app.

- Formula: Ei = a *  KDLb

- Parameters for organic project type: a = 3.2, b = 1.05

- Ei = 3.2 * (0.848) {1.05} ≈ 3.2 x 0.841 = 2.69 person-months.

### Step B: Effort Adjustment Factor (EAF)

Account for higher reliability.

- Required Software Reliability: High (1.15).

- Complexity: Nominal (1.00).

- Total EAF = 1.15 * 1.00 = 1.15

### Step C: Final Effort (E)

- E = EAF x Ei = 1.15 *  2.69 =  3.09 person-months.

## 4. Schedule and Resource Planning

Now we calculate the project duration (D) in months and the required personnel (P) .

### Project Duration (D)

- Formula: D = 2.5 * E 0.38  (for organic projects)

- D = 2.5 * (3.09)0.38 =  2.5 * 1.53 = 3.8 months.

### Staffing Requirements (P)

- Formula: P = E/D

- P = 3.09/3.8  =  0.81 people.

## 5. Final Summary

| Category | Value | Method/Source |
| --- | --- | --- |
| Functional Size | 16 Function Points | Widget Point Analysis |
| Technical Size | 848 LOC | Java Conversion (53 LOC/FP) |
| Total Effort | 3.09 Person-Months | COCOMO (Organic) |
| Total Duration | 3.8 Months | Schedule Plan Formula |
| Staffing | ~1 Developer | Average Demand (P) |

Cost Estimation:

Total costs would comprise Personal-Cost (Salary based on 3.09 PM), Software/Licenses, and Infrastructure . If assuming a standard Swiss developer salary of 10,000 CHF/month (really a guess), the estimated personal cost would be approximately 30,900 CHF.

For Software & LicensesApple/Google Dev Accounts, IDEs, development tools around 400 CHF.

For Infrastructure Backend cloud hosting, database, data storage (6-month runway)around  700 CHF

Total Estimated Cost 32,000 CHF